## Slide 1
PDS4 training workshop
4-8 November 2024, ESAC, Spain
PSA Archive reviews

## Slide 2: Overview
What is a PSA Archive review?
  It is a mandatory process chaired by the PSA Science Lead and involving the science ground segment, instrument teams, internal and external reviewers
  Scope: instrument data and documentation hosted in the PSA are the best possible
    All PSA data should be certified before public release
  It is included in the Archiving Plan or equivalent document, work packages etc.
    The Archive scientists will give specifics for each review to the relative teams
How many and when?
  At least 2 reviews: one before science phase and one toward post-operations
    Extended missions may want to perform one or more intermediate reviews
    Short cruise missions should complete the first review before launch
What is under review exactly?
  Normally, 1 instrument at a time will be reviewed but sub-instruments can be considered
    But beware of overheads due to multiple reviews
    Last review would likely be multi-instruments
  Data: science, housekeeping, ancillary (e.g. geometry, browse products etc.)
    science products should be at least up to PDS4 calibrated processing level
  Documentation for the science community (User guides, tutorials etc.)

## Slide 3: Step 0 – Are we ready?
All products must be ingested in the PSA well before the start of the review
  Important: they will remain private at least until after the review is complete
All documentation (user guides especially, calibration information/products, etc.) must be available and in good shape
Both of the above require iterations with your archive scientist
Time availability over a few months minimum as typical timeline is:
  ~1 month for the reviewers to raise RIDs (Review Item Discrepancies)
  2-4 weeks for the P.I. teams and ESA to respond
  + Implementation time
  ➡️ Exact schedule depends on the review
    ➡️ Typical total review time is at least a few months
When all is ready, the PSA Science lead will select independent reviewers expert in either PDS4 or the instrument science, eliciting suggestions from the Project Scientist or the instrument teams

## Slide 4: Step 1 - The reviewers
The reviewers will receive:
  a datapack (procedure+instrument documentation+selected data)
  temporary access to all PSA data for the instrument under review
  access to the RID system
They must ensure that
  Documentation is clear and complete
  The data products are technically well constructed and of scientific good quality
  The steps to go from lower to higher processing levels are well explained and calibrated products are reproducible with existing documentation and calibration
  The metadata are well defined in terms of usability and usefulness
Issues/requests can be raised as a RID in a dedicated system (e.g. gitlab). For example:
  Issues with data structure, lack of metadata, typos, insufficient/unclear documentation, calibration issues

## Slide 5: Step 2 -The instrument team and ESA Science Ground Segment
At the end of the review period, interested staff from the instrument team and ESA will be given access to the RID system
The instrument archive scientist will assign the RIDs to the appropriate person
  But all with said access can actively participate in offline discussions in the RIDs themselves
All RIDs must be addressed during the dedicated time and a panel telecon to discuss the most controversial RIDs may be called to find a way forward
Timeline/deadline for the specific implementations should be given in the RIDs and ideally it should not be more than a few months at most

## Slide 6: Step 3 – The end(-ish)
With all RIDs closed and implementations in place and depending on mission phase (early, middle, post-operations), the instrument archive scientist may
  organise a partial or complete deletion and/or reprocessing of the PSA with the updated pipeline
  a further consolidation of the archival content and/or documentation as needed
  any other item requested by the reviewers
To note for the first review:
  The matter of releasing the data publicly will be addressed toward the end
  of the review
    The question will be posed to the P.I. and discussed with the Project
    Scientist
    DOIs (Digital Object Identifiers) linked to data collections will be generated

## Slide 7: Takeaways and some tips
The mandatory review process and follow-up implementations can take a while
  add it to your roadmap and try to respect it
  do not plan reviews right before science phase to avoid last minute panic
  take advantage of long cruises
  data and documentation must be in the PSA well before review, so allow for
  time to interact with your archive scientist
Use it! The reviewers will look with fresh eyes ➡️ they can bring in new ideas
Important: The review must be passed, otherwise the data in the PSA are not certified. However:
  ESA can make the PSA data public even if the review is not successful but the data will be labelled as Not Certified and this information made visible in the PSA User Interfaces
A successful review will highlight your hard work in the face of the science community
(more citations, networking, papers, funding possibilities)